## Summary
Project CALIFORNIA MARKETING |  | https://qasvus.wixsite.com/ca-marketing
Summary
Overall progress of the QA cycle(Ontime, delayed, Stopped)
|  | Total number of test cases | 9
|  | Number of testers | 1
|  | Test cycle duration | 1 day
Status for
|  | Number of test cases planned | 5
|  | Number of test cases executed | 9
Number of test cases executed overall
|  | Number of defects encountered today | 3
|  | Number of defect encountered so far | 3
|  | Number of critical defects- still open | 3
Overall status
|  | Number of test cases planned | 9
|  | Number of test cases executed | 9
|  | Pass Percentage of the defects | 66.67%
|  | Defects density | 3.33 per day
|  | Critical defects percentage | 33.33%

## Detail status
Project CALIFORNIA MARKETING |  | https://qasvus.wixsite.com/ca-marketing
Detail status
Scenarios | Script | Script step | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Priority | Status
Verify user can enter address only with a correct First Name | Check The User’s Personal Account Address Menu functionality | Verify that list 'My addresses' is showing and addresses removable if are present | 11.22.2021 | Pass
|  | Verify that the first new address with correct values is added | 11.22.2021 | Pass
|  | Verify that the second new address with correct values is added and set as default | 11.22.2021 | Pass
|  | Verify that changing values in second new address is available | 11.22.2021 | Pass
|  | Verify that removing of the second new address is available | 11.22.2021 | Pass
|  | Verify that the adddress with incorrect First name (numbers) is not added | 11.22.2021 | Fail | Address with incorrect First Name such as1234567890 is added in the list | High | Open
|  | Verify that the adddress with incorrect First name (special characters) is not added | 11.22.2021 | Fail | Address with incorrect First Name such as !@#$%^&*() is added in the list | High | Open
|  | Verify that the adddress with incorrect First name (empty) is not added | 11.22.2021 | Pass
|  | Verify that the adddress with informal First name (a lot of the same letter) is not added | 11.22.2021 | Fail | Address with informal First Name such as aaaaaaaaaaaaaaaa… is added in the list | High | Open

## Bug report
Project CALIFORNIA MARKETING
Bug report | https://qasvus.wixsite.com/ca-marketing
TC | Actual result | Priority | Status | QA
TC - 006 | Address is added in the list with First Name 1234567890 | High | Open | Vadim Trefilov
TC - 007 | Address is added in the list with First Name !@#$%^&*() | High | Open | Vadim Trefilov
TC - 009 | Address is added in the list with First Name aaaaaaaaaaaaaaaaa… | High | Open | Vadim Trefilov